## DCIP Cover Page
LEA Name: | Mount Vernon City School District | ENTER DATA INTO ALL YELLOW CELLS.
BEDS Code: | 660900010000
2018-2019 District Comprehensive Improvement Plan (DCIP)
Contact Name | Dr. Waveline Bennett-Conroy | Title | Assistant Superintendent of School Improvement
Phone | 914-665-5246 | Email | wbennett@mtvernoncsd.org
Website for Published Plan | www.mtvernoncsd.org
APPROVAL OF THIS PLAN BY THE SUPERINTENDENT AND BOARD OF EDUCATION (IN NEW YORK CITY, THE CHANCELLOR OR THE CHANCELLOR’S DESIGNEE) IS MANDATORY.
Implementation is required no later than the first day of regular student attendance.
Signatures confirm the respective parties certify that the DCIP addresses all of the required components of the ESEA Flexibility Waiver as detailed on page 1 of this document and understand that any significant modification of the school district’s approved plan require the prior approval of the commissioner.
THE SIGNATURES BELOW CONFIRM APPROVAL.
Position | Signature | Print Name | Date
Superintendent |  | Dr. Kenneth R. Hamilton | 2018-07-07
President, B.O.E. / Chancellor or Chancellor's Designee |  | Ms. Wanda White | 2018-07-07

## Assurances
Statement of Assurances
By signing this document, the Local Education Agency certifies that:
X | 1. The District Comprehensive Improvement Plan (DCIP) has been developed in consultation with parents, school staff and others in accordance with the requirements of Shared-Decision Making (CR 100.11) to provide a meaningful opportunity for stakeholders to participate in the development of the plan and comment on the plans before they are approved.
X | 2. The District Comprehensive Improvement Plan (DCIP) has been formally approved by the school board and will be made widely available through public means, such as posting on the Internet, distribution through the media and distribution through public agencies.
X | 3. The District Comprehensive Improvement Plan (DCIP) will be implemented no later than the beginning of the first day of regular student attendance.
X | 4. A comprehensive systems approach will be established to recruit, develop, retain and equitably distribute effective teachers and school leaders as part of the implementation of the Annual Professional Performance Review (APPR) system required by Education law §3012(c) and §3012(d).
X | 5. Professional development will be provided to teachers and school leaders that will fully support the strategic efforts described within this plan.
X | 6.Meaningful time for collaboration will be used to review and analyze data in order to inform and improve district policies, procedures, and instructional practices.

## District Leadership Team
District Leadership Team
DISTRICT LEADERSHIP TEAM: The DCIP must be developed in consultation with parents, school staff, and others pursuant to §100.11 of Commissioner’s Regulations. Participants who are regularly involved in your district and school improvement initiatives, such as community organizations or institutes of higher education should be included. By signing below, stakeholders ascertain that, although they may not agree with all components of the plan, they have actively participated in the development and revision of the DCIP.
Instructions: List the stakeholders who participated in developing the DCIP as required by Commissioner’s Regulations §100.18. Provide dates and locations of Local Stakeholder meetings. Boxes should be added as necessary.
Meeting Date(s) | Locations(s) | Meeting Date(s) | Location(s)
2018-07-09 | Supt. Conference Room, Board of Education
2018-07-10 | Supt. Conference Room, Board of Education
2018-07-16 | Supt. Conference Room, Board of Education
2018-07-17 | Supt. Conference Room, Board of Education
2018-07-23 | Supt. Conference Room, Board of Education
2018-07-24 | Supt. Conference Room, Board of Education
Name | Title / Organization |  | Signature
Dr. Kenneth R. Hamilton | Superintendent of Schools, MVCSD
Dr. Jeff Gorman | Deputy Superintendent of Schools, MVCSD
Dr. Waveline Bennett-Conroy | Assistant Superintendent of School Improvement
Dr. Claytisha Walden | Associate Superintendent of Curriculum & Instruction, MVCSD
Mrs. Wanda White | President MVCSD School Board
Dr. Kim Smith | Supervisor, Special Education
Ms. Rachel DePaul | Assistant Director, Special Education
Mrs. Rebecca Jones | Principal, Lincoln Elementary School
Mrs. Sharon Bradley | Principal, Mount Vernon S.T.E.A.M.Academy
Dr. Marguerita G. Circello | Standards Administrator ENL & World Languages, K-12, MVCSD
Mr. Frank Gallo | Standards Administrator ELA & Social Studies 7-12, MVCSD
Dr. Satish Jagnandan | Standards Administrator Math & Science K-12, MVCSD
Ms. Michelle McKitty -Bromley | Coordinator of Family and Community Engagement, MVCSD

## District Info Sheet
District Information Sheet
District Information Sheet
District Grade Configuration | PreK-12 | Total Student Enrollment | 7850 | % Title I Population | 72% | % Attendance Rate | 92%
Racial/Ethnic Origin of District Student Population
% American Indian or Alaska Native | 0% | % Black or African American | 71% | % Hispanic or Latino | 22% | % Asian, Native Hawaiian/Other Pacific Islander | 1% | % White | 5% | % Multi-Racial | 1%
Overall State Accountability Status
Number of Targeted (Focus) Schools | 4 | Number of Comprehensive (Priority) Schools | 2 | Number of Local Assistance Plan Schools |  | Number of Schools in Accountability Status | 11 | Number of Title I SIG 1003(a) Recipient Schools | 9 | Number of Title I SIG 1003(g) Recipient Schools | 2
Did Not Meet Adequate Yearly Progress (AYP) in ELA
|  | American Indian or Alaska Native |  |  |  | X |  | Black or African American
X |  | Hispanic or Latino | [5 empty] | Asian or Native Hawaiian/Other Pacific Islander
|  | White | [5 empty] | Multi-Racial
X |  | Students with Disabilities | [5 empty] | Limited English Proficient
X |  | Economically Disadvantaged
Did Not Meet Adequate Yearly Progress (AYP) in Mathematics
|  | American Indian or Alaska Native |  |  |  | X |  | Black or African American
X |  | Hispanic or Latino | [5 empty] | Asian or Native Hawaiian/Other Pacific Islander
|  | White | [5 empty] | Multi-Racial
X |  | Students with Disabilities | [5 empty] | Limited English Proficient
X |  | Economically Disadvantaged
Did Not Meet Adequate Yearly Progress (AYP) in Science
|  | American Indian or Alaska Native |  |  |  | X |  | Black or African American
X |  | Hispanic or Latino | [5 empty] | Asian or Native Hawaiian/Other Pacific Islander
|  | White | [5 empty] | Multi-Racial
X |  | Students with Disabilities | [5 empty] | Limited English Proficient
X |  | Economically Disadvantaged
Did Not Meet Adequate Yearly Progress (AYP) for Effective Annual Measurable Objective
Limited English Proficient

## Overview
| DCIP Plan Overview | REVIEWER FEEDBACK
In this section, the district must describe the development of the plan, the degree to which the previous school year's DCIP was successfully implemented, overall improvement mission or guiding principles at the core of the strategy for executing the mission/guiding principles, the key design elements of the DCIP, and other unique characteristics of the plan (if any), and provide evidence of the district’s capacity to effectively oversee and manage the improvement plan.
The DCIP must be made widely available through public means, such as posting on the Internet, by the district. The Overview will serve as the at-a-glance summary of how the district will use various funding sources to improve student achievement. A complete overview will address the following:
1. Rate the degree to which the District achieved the goals identified in the previous year's District Comprehensive Improvement Plan (Mark with an "X").
Limited Degree (Fewer than 20% of goals were achieved.)
Partial Degree (Fewer than 50% of goals were achieved.)
X | Moderate Degree (At least 50% of goals were achieved.)
Major Degree (At least 90% of goals were achieved.)
2. Rate the degree to which the District successfully implemented the activities identified in the previous year's DCIP (Mark with an "X").
Limited Degree (Fewer than 20% of activities were carried out.)
Partial Degree (Fewer than 50% of activities were carried out.)
X | Moderate Degree (At least 50% of activities were carried out.)
Major Degree (At least 90% of activities were carried out.)
3. Rate the degree to which the activities identified in the previous year's District Comprehensive Improvement Plan impacted academic achievement targets for identified subgroups (Mark with an "X").
Limited Degree (No identified subgroups improved achievement.)
Partial Degree (Some of the identified subgroups improved achievement.)
X | Moderate Degree (A majority of identified subgroups improved achievement.)
Major Degree (All identified subgroups improved achievement.)
4. Rate the degree to which the activities identified in the previous year's DCIP increased Parent Engagement (Mark with an "X").
Limited Degree (There was no increase in the level of Parent Engagement.)
Partial Degree (There was a minor increase in the level of Parent Engagement.)
X | Moderate Degree (There was modest increase in the level of Parent Engagement.)
Major Degree (There was a significant increase in the level of Parent Engagement.)
5. Rate the degree to which the activities identified in the previous year's District Comprehensive Improvement Plan received the funding necessary to achieve the corresponding goals (Mark with an "X").
Limited Degree (Fewer than 20% of planned activities were funded.)
Partial Degree (Fewer than 50% of planned activities were funded.)
X | Moderate Degree (At least 50% of planned activities were funded.)
Major Degree (At least 90% of planned activities were funded.)
6. Identify in which Tenet the district made the most growth during the previous year (Mark with an "X").
Tenet 1: District Leadership and Capacity
Tenet 2: School Leader Practices and Decisions
X | Tenet 3: Curriculum Development and Support
Tenet 4: Teacher Practices and Decisions
Tenet 5: Student Social and Emotional Developmental Health
Tenet 6: Family and Community Engagement
7. Identify in which Tenet identified schools made the most growth during the previous year (Mark with an "X").
Tenet 1: District Leadership and Capacity
X | Tenet 2: School Leader Practices and Decisions
Tenet 3: Curriculum Development and Support
Tenet 4: Teacher Practices and Decisions
Tenet 5: Student Social and Emotional Developmental Health
Tenet 6: Family and Community Engagement
In reflecting on the PREVIOUS YEAR'S PLAN:
• Describe the most significant positive impact(s) that resulted from the previous year’s plan (may include such examples as specific changes in adult behavior and/or measurable changes in student outcomes).
There was a district wide increase in combined unweighted performance index on the NYSED assessments in ELA and math. District-wide professional development (targeted and tiered) has increased collaboration and evidence of effective practices in classrooms.
• Describe all mid-course corrections to the previous year’s plan in response to data review and needed adjustment. Include details of current impact and expectations for sustainability moving forward.
Surveys were conducted to measure the impact of the previous year's plan with staff, students and their families. Changes were made in professional development offerings and parent university to better address identified needs.
In developing the CURRENT YEAR'S plan:
• List the highlights of the improvement initiatives described in the current DCIP.
The plan more evenly distributes responsiblities across the various departments in central office, ensuring a greater ability to follow through.
• List the identified needs in the district that will be targeted for improvement in this plan.
There is a continued need to ensure all sub groups meet AYP.
• State the mission or guiding principles of the district and describe the relationship between the mission or guiding principles and the identified needs of the district.
It is the mission of the Mt. Vernon City School District (MVCSD) to create a sense of urgency in partnership with members of its community in a journey to restore, rebuild and rebrand the district so that stakeholders are partners in providing all students with an exceptional educational experience. The mission clarifies the guiding principles of the district and the expected outcome of our work within the community. It was developed based on the needs of the district and feedback from members of the school community.
• List the student academic achievement targets for the identified subgroups in the current plan.
AYP and/or safe harbor for each subgroup on all NYSED assessments.
• Describe how organizational structures will drive strategic implementation of the mission/guiding principles.
Each department will support each school with their respective needs statements. Schools will support one another within a newly developed PLC structure, to occur on a monthly basis.
• List anticipated barriers that may impact the ability to accomplish the mission or guiding principles and how those barriers will be addressed.
Anticipated barriers include handling the many components of change, designed to promote growth in the district in meeting its mission. These barriers will be addressed by openly communicating in cabinet any potential issues or concerns.
• Describe the professional development opportunities that will be provided to teachers and school leaders and the rationale for each opportunity.
Professional development will occur in each school during the faculty and curriculum meetings. A year long professional development series on Superintendent Conference Days will further support teachers in self selected areas.
• List all methods of dialogue that district leaders will implement to strengthen relationships with school staff and the community.
Regular meetings between the superintendent and/or his designee will engage school leaders in conversations about their progress. Structures such as Parent/Teacher Council Meetings and Special Education Advisory Council meetings.
• List all the ways in which the current plan will be made widely available to the public.
The plan will be posted on the district web page. School leaders will also be encouraged to share this information in their new school year orientations for families.

## PS Reform Model
For Districts with Priority Schools: Whole School Reform Model | REVIEWER FEEDBACK
1. Provide an overview of the district’s overall plan and approach to district and school redesign and its desired impact on the targeted all-school group or sub-groups. In this overview, describe how the school redesign is connected to the larger district strategy and approach. In addition, provide the proposed school’s vision, mission, key partnership organizations, key design elements of the educational program, other unique characteristics of the program, if any, and discussion of the district/partner(s) capacity to effectively support and oversee the proposed school(s).
2.The district must demonstrate that it has the capacity to plan for, implement, and monitor school-level redesign efforts, including the provision of adequate resources and related support in order to effectively support the site-based launch, governance, and implementation of the proposed school. The district must also demonstrate a critical and honest assessment of structural/systems gaps and needs, as well as student achievement gaps and needs.
A. Student Population and Needs. Using statistics and descriptive language, describe the population of students that the LEA serves and any specific unique needs by sub-group such as students with disabilities, English language learners, and students from households that are eligible for free or reduced lunch. Identify the school(s) student population, including sub-groups, to be served by the school-redesign, and describe any unique needs of these populations. In addition, describe the policies for students who choose to enroll or exit the newly designed school.
B. District Systems and Structural Needs. Describe the district’s approach to turning around the underperforming school(s), the theory of action guiding district efforts and the key district strategies. Describe the district’s core challenges and issues related to turning around the school(s), based on data and the district’s assessment of its current systems, structures, and policies for supporting underperforming schools. Identify and describe current systems and structural strengths, and weaknesses related to providing school-level site-based governance, human capital pipelines and development, education and instructional programs, school-level, site-based fiscal autonomy and management, and facilities acquisition and use.
C. District Systems and Structures to Monitor and Support Implementation. Describe the structures or other processes to be used to support and monitor implementation of school-level redesign efforts. Describe how the district will ensure that the identified school will receive ongoing, intensive support from the district or designated external partner organization(s). Describe how the district will monitor the implementation of the selected intervention at each identified school and how the district will know that planned interventions and strategies are working. Specifically, please describe how the district will provide for review of data related to implementation benchmarks and measurable annual goals. Discuss the frequency, type, and extent of monitoring activities and who will be responsible.

## Leading Indicators
Common Leading Indicators Worksheet
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. For each leading indicator, enter a "Y" into the cell for each applicable SOP for which that indicator will be used. | Tenet 1 | SOP 1.2 | SOP 1.3 | SOP 1.4 | SOP 1.5 | Tenet 2 | Tenet 3 | Tenet 4 | Tenet 5 | Tenet 6 | SOP 1.1. | SOP 1.2. | SOP 1.3. | SOP 1.4. | SOP 1.5 | SOP 2.1. | SOP 3.1. | SOP 4.1. | SOP 5.1. | SOP 6.1.
Student Growth Percentile for Low-Income Students
Student Average Daily Attendance | [18 empty] | Student Average Daily Attendance | bar: Tenet 5
Student Drop-Out Rate | [18 empty] | Student Average Daily Attendance
Student Credit Accruals (HS Students) | [18 empty] | Student Average Daily Attendance
Student Completion of Advanced Coursework | [18 empty] | Student Average Daily Attendance
Student Suspension Rate (Short-Term / Long-Term) | [18 empty] | Student Average Daily Attendance
Student Discipline Referrals | [18 empty] | Student Average Daily Attendance
Student Truancy Rate | [18 empty] | Student Average Daily Attendance
Student Performance on January Regents Exams | [18 empty] | Student Average Daily Attendance
Student Participation in ELT Opportunities | [18 empty] | Student Average Daily Attendance
Minutes of Expanded Learning Time (ELT) Offered | [18 empty] | Student Average Daily Attendance
Teacher Average Daily Attendance Rate | [18 empty] | Student Average Daily Attendance
Teachers Rated as "Effective" and "Highly Effective" | [15 empty] | Teachers Rated as "Effective" and "Highly Effective" |  | Teachers Rated as "Effective" and "Highly Effective" | Student Average Daily Attendance | bar: Tenet 2; Tenet 4
Teacher Attendance at Professional Development | [15 empty] | Teachers Rated as "Effective" and "Highly Effective" |  | Teachers Rated as "Effective" and "Highly Effective" | Student Average Daily Attendance
Parent Attendance at Workshops | [15 empty] | Teachers Rated as "Effective" and "Highly Effective" |  | Teachers Rated as "Effective" and "Highly Effective" | Student Average Daily Attendance | Parent Attendance at Workshops | bar: Tenet 6
Parent Participation in District/School Surveys | [15 empty] | Teachers Rated as "Effective" and "Highly Effective" |  | Teachers Rated as "Effective" and "Highly Effective" | Student Average Daily Attendance | Parent Attendance at Workshops Parent Participation in District/School Surveys | bar: Tenet 6
Principals Rated as "Effective" and "Highly Effective" | [10 empty] | Principals Rated as "Effective" and "Highly Effective" |  |  |  |  | Teachers Rated as "Effective" and "Highly Effective" |  | Teachers Rated as "Effective" and "Highly Effective" | Student Average Daily Attendance | Parent Attendance at Workshops Parent Participation in District/School Surveys | bar: Tenet 1
Student Performance on i-Ready assessments (Beginning-of-Year & End-of-Year) | [10 empty] | Principals Rated as "Effective" and "Highly Effective" |  |  |  |  | Teachers Rated as "Effective" and "Highly Effective" | Student Performance on i-Ready assessments (Beginning-of-Year & End-of-Year) | Teachers Rated as "Effective" and "Highly Effective" | Student Average Daily Attendance | Parent Attendance at Workshops Parent Participation in District/School Surveys | bar: Tenet 3
Student Performance on NYSED ELA and mathematics tests | [10 empty] | Principals Rated as "Effective" and "Highly Effective" |  |  |  |  | Teachers Rated as "Effective" and "Highly Effective" | Student Performance on i-Ready assessments (Beginning-of-Year & End-of-Year) | Teachers Rated as "Effective" and "Highly Effective" | Student Average Daily Attendance | Parent Attendance at Workshops Parent Participation in District/School Surveys
Student Performance on June Regents Exams | [10 empty] | Principals Rated as "Effective" and "Highly Effective" |  |  |  |  | Teachers Rated as "Effective" and "Highly Effective" |  | Teachers Rated as "Effective" and "Highly Effective" | Student Average Daily Attendance | Parent Attendance at Workshops Parent Participation in District/School Surveys
Professional Learning | [10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Parent Participation in school based activities. | [10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Tenet 1
Tenet 1: District Leadership and Capacity |  |  | REVIEWER FEEDBACK
Tenet 1: District Leadership and Capacity |  | The district examines school systems and makes intentional decisions to identify and provide critical expectations, supports and structures in all areas of need so that schools are able to respond to their community and ensure that all students are successful. | The district examines school systems and makes intentional decisions to identify and provide critical expectations, supports and structures in all areas of need so that schools are able to respond to their community and ensure that all students are successful.
B1. Most Recent DTSDE Review Date: |  | 2013-2014
B2. DTSDE Review Type: |  | IIT Led Review
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Needs Statement: Create a clear and concise statement that addresses the primary need(s) to be addressed. Be sure to incorporate feedback from the most recent DTSDE review and other applicable data. |  | The district recognizes the need to create and implement systems and structures to ensure consistent practices with regard to data analysis, curriculum planning and implementation, instructional practices, professional development, attendance structures and character education. | As you begin, consider including curriculum planning in addition to curriculum implementation.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Needs Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | District leaders will monitor the school level implementation various structures to address consistent practices in data analysis, instruction, professional development, student attendance, teacher feedback and character education. During the 2018-19 school year, at least 85% of principals will receive an average rating of “Effective” or “Highly Effective” on the Multi-dimensional Professional Performance Rubric Domain 2-School Culture and Instructional Program.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Principals Rated as "Effective" and "Highly Effective", Parent Participation in District /School Surveys, and Student participation in ELT opportunities. | Consider using additional measures throughout the school year.
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Specifically describe what each planned activity is; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and the intended impact of each activity. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-07-01 | 2018-09-01 | The Superintendent, Deputy Superintendent, Assistant Superintendent of Business, Assistant Superintendent of Human Resources, Assistant Superintendent of School Improvement, Associate Superintendent of Curriculum and Instruction, and the Finance Manager will work collaboratively to create an organizational chart that delineates specific roles and responsibilities within the MVCSD in an effort to clarify and streamline systems of operations within the district.
2018-08-23 | 2018-08-28 | The 2018-19 New Teacher Orientation (NTO), hosted by the Deputy Superintendent, Associate Superintendent of Curriculum and Instruction, the Assistant Director of Special Education, Standards Administrators and Professional Development Coordinators, is an annual orientation designed to familiarize newly hired teachers with district expectations and various resources to support them.
2019-01-01 | 2019-05-01 | The district hiring fair hosted by Assistant Superintendent for Human Resources is designed to ensure that highly qualified candidates are actively recruited by the MVCSD.
2018-09-01 | 2019-06-30 | The monthly PLC Meetings hosted by the Associate Superintendent of Curriculum and Instruction are designed to develop instructional leadership capacity, promote teaching and learning, and develop data and evidence‐based practices among building leaders.
2018-09-01 | 2019-06-30 | The New Teacher Mentoring Program sponsored by the MVFT Representatives, in conjunction with the Educational Leadership Consortium, will continue its work to ensure that new teachers have access to the accumulated instructional knowledge and expertise of their colleagues in ways that contribute to student success.
2018-09-01 | 2019-06-30 | Instructional Rounds conducted by the Superintendent, Deputy Superintendent, Assistant Superintendents, Associate Superintendent of Curriculum and Instruction, Standard Administrators, Principals, Assistant Principals, Special Education Supervisors, Department Administrators, as well as coaches and teachers are meant to enhance teachers' pedagogical skills and develop a culture of collaboration. The goal of instructional rounds is for observing teachers to compare their own instructional practices with those of the teachers they observe. The chief benefit of this approach resides in the discussion that takes place among observing teachers at the end of the observation as well as in subsequent self-reflections. The monthly progress should be evidenced by the following; 1)teacher as a facilitator, 2) increased project based learning, 3) coherence of instruction, and 4) implementation fidelity. | At this stage, reflect on what progress you hope to make for the Instructional Rounds on a monthly basis between September and June.
2018-09-01 | 2019-11-01 | Principals who receive composite scores in the "Ineffective" or "Developing" ranges are required to have an improvement plan. The Principal Improvement Plan (PIP) is designed for the superintendent to collaborate with principals to systematically improve their leadership practices as it relates to student achievement.
2018-09-01 | 2019-05-01 | Teachers who receive composite scores in the "Ineffective" or "Developing" ranges are required to have an improvement plan. The Teacher Improvement Plan (TIP) is designed for teacher to identify areas in need of improvement and to develop action plans designed to improve their teaching performance. This plan is with the support of the school principal in a concerted effort to raise student achievement.
2018-09-01 | 2019-04-01 | Tenure Defense Rounds will be conducted by the Superintendent in conjunction with building Principals that have probationary teachers with tenure appointment dates in the 2018-19 school year. This process is designed to ensure that probationary teachers recommended for tenure meet the high expectations the Superintendent holds in order for them to continue their careers in the district.
2018-09-01 | 2019-06-30 | Year-long Professional Development activities will be implemented collectively by the Deputy Superintendent, Associate Superintendent of Curriculum and Instruction, the Assistant Superintendent for School Improvement, the Assistant Director of Special Education, the Standards Administrators, and the PD Coordinators for the benefit of all MVCSD staff. PD will take place on all Superintendent's Conference Days and Early Release Days. The PD Plan includes specific trainings identified by teachers as an area of need. The trainings are designed to enhance teacher's ratings and ultimately positively impact student achievement. In keeping with the ESSA Act, PD will most specifically focus on achievement across all content areas and will positively impact chronic absenteeism, graduation rates, ELL proficiency, and college, career, and civic-minded pursuits.
2018-09-01 | 2019-06-30 | Superintendent's Cabinet Meetings will be conducted by the Superintendent and his respective cabinet members. These meetings will include all district administrators and others as needed. These monthly meetings are designed to evaluate policies, support administrators, and enhance decision making mechanisms.
2018-09-01 | 2019-06-30 | Data Meetings will be supervised by the Assistant Superintendent for School Improvement along with the Associate Superintendent of Curriculum and Instruction and will take place in the fall and early spring. These meetings are designed to support school principals in understanding their needs according to NYSED data and to establish SMART goals based on leading indicators. The second meeting is designed to review the progress made by reviewing the SMART goals and assessing what areas have been effective and where additional supports and interventions are warranted.
2018-09-01 | 2019-06-30 | Character Education professional development will focus on school-wide systemic change to prepare educators and school leaders to create safe, healthy, high-performing schools, while inspiring students to reach their full potential as global citizens.
2018-10-01 | 2019-03-01 | School Budget Defense Rounds conducted by the Superintendent, Deputy Superintendent, the Assistant Superintendents, and the Associate Superintendent of Curriculum and Instruction will ensure accessibility and equity of resources to support all students.
2018-09-01 | 2019-05-30 | Based on student achievement in core subjects and non-academic indicators such as chronic absenteeism, schools identified as “Comprehensive Support and Improvement” and “Targeted Support and Improvement” will participate annually in diagnostic visits (Pre DTSDE and DTSDE). This process compares schools’ practices to optimize conditions of learning, as defined by the Diagnostic Tool for School and District Effectiveness (DTSDE) rubric.

## Tenet 2
Tenet 2: School Leader Practices and Decisions |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 2.1 - The district works collaboratively with the school to provide opportunities and supports for the school leader to create, develop and nurture a school environment that is responsive to the needs of the entire school community. | SOP 2.1 - The district works collaboratively with the school to provide opportunities and supports for the school leader to create, develop and nurture a school environment that is responsive to the needs of the entire school community.
B1. Most Recent DTSDE Review Date: |  | 2013-2014
B2. DTSDE Review Type: |  | IIT Led Review
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Needs Statement: Create a clear and concise statement that addresses the primary need(s) to be addressed. Be sure to incorporate feedback from the most recent DTSDE review and other applicable data. |  | The district needs to support schools in an equitable manner to support its vision for improvement and attainment of building/district goals. Based on the previous DTSDE visit and Danielson Framework, the following areas have been identified for support: tiered professional development for success student (differentiation), effective use of data, and monitoring of outcomes so that efforts translate into impact and ensure a learning environment that promotes success for all students.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Needs Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | At least 85% of teachers will receive an average rating of “Effective” or “Highly Effective” on the Danielson Frameworks - Domain 3: Purposeful Instruction. | As you begin, consider including goals to support tiered professional development for student success (differentiation), effective teacher use of data, and developing a monitoring system with outcomes that promote success for all students.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Teachers Rated as “Effective” and “Highly Effective” | Consider using interim measures during the course of the school year.
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Specifically describe what each planned activity is; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and the intended impact of each activity. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-05-18 | 2018-06-18 | The MVCSD Department of Curriculum and Instruction, the Office of School Improvement, along with the district's PD coordinators will continue to use a Professional Development Needs Survey for teachers and administrators in order to gain insights on professional development that will focus on the tenets of the newly adopted ESSA Act. As such, Professional development will now address increased student achievement in all core subjects, as well as graduation rates, ELL proficiency, chronic absenteeism, and college, career, and civic readiness. In particular, professional development will focus on infusing STEAM in the curriculum, SDI and EDI as it relates to Special Education, Guided Reading, AVID & AVID EXCEL, as well as Curriculum Based Aligned Instruction (CBAL) for ENL. | During implementation, include activities to address the needs identified as areas in need of support, including thinking about professional development as a tool to support teachers in the work of monitoring student progress.
2018-06-17 | 2019-06-30 | Beginning in June 2018, district leaders will meet monthly with school leaders to help each leader establish strategic short- and long- term SMART goals for increasing student achievement, as outlined in the School Comprehensive Education Plan (SCEP) and which are embraced within the district's theory of action. Furthermore, district leaders will discuss the newly adopted ESSA Accountability System and assess current trends in data so that building leaders can craft SMART goals that specifically focus on these revised indicators. District leaders will also provide professional development to school administrators around observation, evaluation, data analysis, and the use of common planning time. | Please consider the outcomes that you hope to accomplish on a monthly basis between September and June, as a result of the activity.
2018-09-17 | 2019-06-30 | Data specialists will continue their work with school leaders aligning assessments with instruction and identifying proficiency targets by grade level and subject area. | Reflect on getting weekly and/or monthly updates showing progress towards the goal.
2018-01-01 | 2018-08-30 | The Office of Curriculum and Instruction, School Improvement, and the Director of Guidance will continue their work to implement systemic changes necessary in our schools (i.e., master scheduling, grade configurations, and course offerings) and at the district level to improve student academic achievement via instructional rounds, relevant professional development and other building indicator data.
2018-09-12 | 2018-10-17 | Principals will lead professional development with their respective staffs around the ESSA Act and how it will impact the goals and action plans outlined in their SCEP/SPSE plans. They will work to develop a comprehensive understanding of the ESSA plan and its far reaching implications, as well as provide tiered professional development based on need. | AT this stage, t think about including tiered professional development activities that promote student success.

## Tenet 3
Tenet 3: Curriculum Development and Support |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 3.1 - The district works collaboratively with the school(s) to ensure CCLS curriculum that provide 21st Century and College and Career Readiness skills in all content areas and provides fiscal and human resources for implementation. | SOP 3.1 - The district works collaboratively with the school(s) to ensure CCLS curriculum that provide 21st Century and College and Career Readiness skills in all content areas and provides fiscal and human resources for implementation.
B1. Most Recent DTSDE Review Date: |  | 2013-2014
B2. DTSDE Review Type: |  | IIT Led
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Needs Statement: Create a clear and concise statement that addresses the primary need(s) to be addressed. Be sure to incorporate feedback from the most recent DTSDE review and other applicable data. |  | The district needs to continue to provide consistent and effective feedback support to modify curriculum and instruction to meet the needs of ALL subgroups to make AYP. | Reflect on what curricular and instructional modifications need to address students in specific subgroups.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Needs Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | During the 2018-19 school year, at least 85% of students will demonstrate growth of at least 20 points on their I-Ready assessments (Beginning-of-Year & End-of-Year) in grades 2-9 ELA and mathematics. Constant feedbback will be given based on baseline assessments and ongoing progress monitoring. | Please think about including targets for the district to establish a goal to provide consistent and effective feedback to teachers as they modify curriculum and instruction to meet the needs of students in ALL subgroups.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | i-Ready assessments (Beginning-of-Year & End-of-Year), PLC meetings, Faculty and Curriculum meetings, and review of teachers' lesson plans. | As you develop indicators, consider including additional measures, such as monthly, that the district can use to gauge teachers' progress modifying curriculum and planning for instruction for all students.
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Specifically describe what each planned activity is; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and the intended impact of each activity. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-07-01 | 2018-08-31 | The district will rigorously review, modify and develop curriculum maps to provide multiple points of access/scaffolds for all students, small group instruction, and greater integration between subject areas.
2018-09-01 | 2018-09-30 | Data specialists will continue their work with school leaders and data inquiry teams identifying proficiency targets by grade level and subject area.
2018-09-01 | 2019-06-30 | The Office of Curriculum and Instruction, which includes the Associate Superintendent of Curriculum and Instruction, Standard Administrators, SWD Supervisors, and ENL, SWD, ELA, and Math Coaches, along with consultants provided by the Office of School Improvement, will support school-based teams in the modifications and adaptations of curriculum for all students and subgroups. These supports will occur during Curriculum, Data and PLC meetings to establish short and long term curriculum goals. In addition, professional development will concentrate on setting rigorous, standards-based learning targets, student engagement and the assessment of student learning. | As you begin implementation, please think about how the professional learning plan enables the district to make progress towards the goal of supporting teachers in their work to address student needs.
2018-09-01 | 2019-06-30 | The Associate Superintendent of Curriculum and Instruction will conduct Principal and Assistant Principal PLCs to support leadership development in providing teacher feedback through instructional rounds, book study, workshops, etc.
2018-09-01 | 2019-06-30 | The Office of Curriculum and Instruction, Office of School Improvement and Department of Special Education will provide support and oversight in curriculum implementations (Balanced Literacy, Journeys, Collections , enVisionmath 2.0, HMH Social Studies, Orton-Gillingham Multi-Sensory Reading Instruction and STEM Connects).
2018-10-01 | 2019-06-30 | School leaders will collect, review and provide effective feedback to teachers on the modifications of lessons plans. | During the year, reflect on what curricular and instructional modifications are provided to teachers in order to address students in specific subgroups.
2018-10-01 | 2019-06-30 | The Office of Curriculum and Instruction in collaboration with school leaders will establish a system that affords teachers the time to meet with ELA/Math coaches and school leaders on weekly basis to discuss student data and identify trends in student learning.
2018-10-01 | 2019-06-30 | The Office of Curriculum and Instruction, Office of School Improvement and Department of Special Education, in conjunction with school-base teams, will identify and focus on priority/high leverage standards during Extended Learning Time (ELT) as part of MVCSD's efforts to extend the school day and school year for all students.
2018-07-01 | 2019-06-30 | MVCSD has partnered with Discovery Education Professional Development to provide dynamic professional learning that combines content, pedagogy and technology to create innovative and engaging learning experiences. The goal is to strengthen teacher effectiveness, empower school leaders and increase student engagement. | During implementation, please think about the professional development process as a tool to support teachers in the work of tracking and monitoring student progress.

## Tenet 4
Tenet 4: Teacher Practices and Decisions |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 4.1 - The district works collaboratively with the school to provide opportunities and supports for teachers to develop strategies and practices and addresses effective planning and account for student data, needs, goals, and levels of engagement. | SOP 4.1 - The district works collaboratively with the school to provide opportunities and supports for teachers to develop strategies and practices and addresses effective planning and account for student data, needs, goals, and levels of engagement.
B1. Most Recent DTSDE Review Date: |  | 2013-2014
B2. DTSDE Review Type: |  | IIT Led Review
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Needs Statement: Create a clear and concise statement that addresses the primary need(s) to be addressed. Be sure to incorporate feedback from the most recent DTSDE review and other applicable data. |  | The District team needs to target professional development around the needs of teachers based on data analyzed from teacher evaluations, instructional walkthroughs and student NYSED assessment data.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Needs Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 30, 2019, there will be a 10% decrease of teachers rated "Ineffective" or "Developing" (APPR Composite Rating) as compared to the 2017-18 school year. | As you look at this goal, please think about professional learning as a tool to support teachers in the work of tracking and monitoring student progress.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Teachers Rated as ""Effective"" and ""Highly Effective", Professional Learning | Consider including additional measures to indicate progress more frequently, such as monthly, at the end of each marking period, quarterly and/or by semester.
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Specifically describe what each planned activity is; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and the intended impact of each activity. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-01 | 2019-06-30 | The MVCSD will continue to support professional development via AVID Summer Institutes in Philadelphia and Dallas for administrators, teachers and Coordinators. | During implementation, consider who will be responsible for completing each activity; who will participate; how often will each activity take place; and the intended impact of each activity.
2018-09-01 | 2019-06-30 | Mt. Vernon STEAM Academy staff will participate in sustained, cutting edge professional development through the Discovery Education. This work will provide an educational approach that integrates Science, Technology, Engineering, the Arts, and Mathematics through project-based learning. | Please think about professional development as a tool to support teachers as they work to track and monitor student progress.
2018-09-01 | 2019-06-30 | Mt. Vernon STEAM Academy will partner with the City University of New York at Lehman College, providing interns from the fields of Science and Math to collaborate with teachers to enhance their pedagogy.
2018-07-09 | 2019-06-30 | In conjunction with New York University, Mt. Vernon STEAM Academy will implement a Robotics Program. The program will introduce rising 9th through 12th high school students to the basics of robotics, mechatronics and programming. Throughout the program, the focus will be on providing extensive hands-on experience to students through a series of activities, tailored especially for challenging young minds and encouraging ‘Out of the Box’ thinking. | Reflect on the progress towards the goal and intended impact of each activity towards building inquiry and problem solving capacity of students..
2018-09-01 | 2019-06-30 | The REACH Program will continue its efforts to bring a Balanced Literacy framework in all K-12 schools in order to improve literacy instruction across the content areas.
2018-09-01 | 2019-06-30 | The MVCSD will continue to offer innovative and challenging Syracuse University Project Advance (SUPA) courses to qualified high school students. The intent is to increase students’ college readiness by providing college readiness tools, programs, and services.
2018-09-01 | 2019-06-30 | MVCSD has partnered with Project Lead The Way (PLW) to provide transformative learning experiences for K-12 students and teachers. The partnership will create an engaging, hands-on classroom environment and empower students to develop in-demand knowledge and skills they need to thrive.
2018-07-09 | 2019-06-30 | Transition to College Readiness (StepUp) is a collaboration between Westchester Community College (WCC) and MVCSD high schools (Thornton HS and MVHS) to help prepare students to enter college without the need for remediation. The StepUp program is designed for students who are on track to graduate but likely to place into developmental English and/or Math in their first year of college. Students enroll in a 12th Grade English or Math class (or both) co-developed by high school and college faculty, and if successful, bypass the WCC Placement test and can enroll directly into the next credit bearing course(s).
2018-09-01 | 2019-06-30 | The Deputy Superintendent, Assistant Supt. of School Improvement, Associate Superintendent of Curriculum and Instruction, the Standards Administrators, the PD Coordinators, and the Department of Special Education, created a yearlong Professional Development Academy providing teachers opportunities to attend targeted workshops to improve instructional practice and thereby increase student achievement. With the emergence of the ESSA Act, professional development will be geared more towards meeting the following revised standards: 1) achievement across the content areas 2) improved graduation rates 3) increased ELL proficiency 4) decreased chronic absenteeism and 5) improved college, career, and civic readiness.

## Tenet 5
Tenet 5: Student Social and Emotional Developmental Health |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 5.1 - The district creates policy and works collaboratively with the school to provide opportunities and resources that positively support students' social and emotional developmental health. | SOP 5.1 - The district creates policy and works collaboratively with the school to provide opportunities and resources that positively support students' social and emotional developmental health.
B1. Most Recent DTSDE Review Date: |  | 2013-2014
B2. DTSDE Review Type: |  | IIT Lead Review
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Needs Statement: Create a clear and concise statement that addresses the primary need(s) to be addressed. Be sure to incorporate feedback from the most recent DTSDE review and other applicable data. |  | There is a need for the District to create a preventative network that nurtures healthy social development for all students while promoting academic progress. | Think about what limits students’ social and emotional development.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Needs Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 1, 2019, there will be 10% decrease in student absences as compared to the 2017-18 school year. In addition, students will take part in character education curriculum, restorative justice practices, MBK and PBIS initiatives in order to nurture healthy social development and good citizenship. | Consider including in the district goal, an outcome that nurtures healthy social development for all students while promoting academic progress.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Student Average Daily Attendance. Student discipline referrals. Student truancy. | Include additional indicators over the course of the school year to assess students' social and emotional health.
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Specifically describe what each planned activity is; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and the intended impact of each activity. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-01 | 2018-11-01 | All staff members will be trained by the District's Counsel and Associate Superintendent of Student Support Services on the Dignity for All Students Act (DASA) and its investigative and reporting processes. Each principal will ensure the appointment of a DASA Coordinator. In addition, they will ensure the DASA process will be conducted with fidelity and in accordance with the law. The school-based clinical team will assist with preventative services to address the needs of affected students.
2018-09-01 | 2019-06-30 | District Representatives will attend Community Network meetings. The Associate Superintendent of Student Support Services, or a designee, will meet with the building leaders to address chronically truant students and refer those facing disciplinary action to community resources. A district consultant will serve as an advisor to this initiative. | At this stage, reflect how activities lead towards healthy social development for all students as they strive towards making academic progress.
2018-09-01 | 2018-11-01 | Under the direction of the Assistant Director of Special Education and the Standards Administrator for Guidance, the school based clinical support teams will facilitate Mental Health Training for all staff members. Additionally, the school based clinical team will develop systems to support social and emotional learning in all classrooms.
2018-10-01 | 2018-12-31 | In an effort to reduce suspensions, building leadership will be provided training in alternatives to suspension and be introduced to Restorative Justice Practices as a framework for building community and for responding to challenging behaviors.
2018-09-01 | 2019-06-30 | Addressing chronic absenteeism is essential in meeting the needs of students who are continually missing school and are subsequently at-risk academically. The MVCSD Attendance Policy will define chronic absenteeism as missing 18 or more days of school. School building and district leadership will identify preventative systems to focus supports on students and families who are approaching this number of absences.
2018-09-01 | 2019-06-30 | Character Education is a way to combat unhealthy behavioral choices and the negative consequences that come with them. Each school will implement the Character Education program which incorporates research and evidence-based strategies. Implementation of the framework will instill academic, social, emotional and ethical values. In addition, it will include mindsets and character traits that will help students reach their academic potential and become engaged, responsible, and productive citizens--all of which coheres with the tenets of the ESSA Act.

## Tenet 6
Tenet 6: Family and Community Engagement |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 6.1 - The district has a comprehensive family and community engagement strategic plan that states the expectations around creating and sustaining a welcoming environment for families, reciprocal communication, and establishing partnerships with community organizations and families. | SOP 6.1 - The district has a comprehensive family and community engagement strategic plan that states the expectations around creating and sustaining a welcoming environment for families, reciprocal communication, and establishing partnerships with community organizations and families.
B1. Most Recent DTSDE Review Date: |  | 2013-2014
B2. DTSDE Review Type: |  | IIT Lead Review
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Needs Statement: Create a clear and concise statement that addresses the primary need(s) to be addressed. Be sure to incorporate feedback from the most recent DTSDE review and other applicable data. |  | There is a need for the district to develop a school-based parent plan which allows families to participate in reciprocal communication with school staff about student academic, social, and emotional development. | As you begin, reflect on what limits reciprocal communication among parents and families to be able to support their student's learning.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Needs Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 30, 2019 the mean responses (based on the End-of-Year K-12 Insight Parent Survey, the percentage of usage of Schoology, Home Access, and Parent Portal) will indicate agreement with the tenets in the Statement of Practice which should yield an increase by at least 10% as compared to the 2017-18 school year. Additionally, by June 30, 2019 parent attendance at workshops will increase by at least 10% as compared to the 2017-18 school year. | Consider developing a goal for each school-based parent plan that allows families to participate in reciprocal communication with school staff about students' academic, social, and emotional development as it relates to academic achievement.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Parent Attendance at Workshops; Parent Participation in District/School Surveys. Parent participation in school based activities. | As you look for indicators, please consider including monthly or additional measures during the school year.
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Specifically describe what each planned activity is; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and the intended impact of each activity. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-01 | 2019-06-30 | The Office of School Improvement will continue to collaborate with the District Webmaster to monitor and maintain the distribution of pertinent information in a timely fashion. This will ensure that every member of the school community remains abreast of district and community-based activities, such as Board Meetings, PTA Meetings, School Activities, NYSED & Tile I Information, Parent Universities, and so forth. | At this stage, reflect on how these activities will lead towards the intended outcome.
2018-09-01 | 2019-06-30 | The FACE Office will create a network of supports and service providers by collaborating with community-based organizations to meet the varied needs of students and their families, such as providing Financial Literacy workshops. The evidence of our impact will be shown by an increase in the number of students and families accessing supports and attending programs.
2018-09-01 | 2019-06-30 | The Assistant Superintendent of School Improvement will provide certified consultants that will train school and community members in a variety of areas, such CPR and Microsoft. This office will also provide trainings through Parent Universities, the Resource Fair and the Mt. Vernon Basics Program. These workshops are formulated based on parent, student and district-based data.
2018-09-01 | 2019-06-30 | The Chief Information Officer will provide training for district staff in using the Home Access Portal as a vehicle to communicate with parents regarding their child's academic performance, attendance, et al.
2018-09-01 | 2019-02-17 | The Annual Parent Involvement Day, which is held in conjunction with the National African American Parental Involvement Committee and the Mount Vernon Parent and Community Forum on Education, will continue to host this annual event in which parents are given an opportunity to attend their children’s classes as well as take part in a number of exciting and highly informative workshops designed to give parents a clearer understanding of how they can best help their children to succeed in school.
2018-09-01 | 2018-09-30 | The FACE Office will develop a protocol on the ways in which school communities can create an inviting school climate and provide a welcome packet for visiting parents, including a community services directory. Teachers will be encouraged to make personal contacts with families through e-mail and phone calls. In addition to the annual Meet and Greet Nights, parents will be invited to attend workshops where they will receive materials on child development and the appropriate milestones and expectations they should meet at each grade level.
2018-09-01 | 2019-06-30 | The District will continue to utilize a cadre of trained Parent Liaisons who work collaboratively with school staff to increase family engagement and community outreach. As part of their work, the parent liaisons will create a Customer Service Survey to ensure that the district provides quality service, relevant information, and addresses issues and complaints promptly so that all stakeholders are full partners in the education of our children.
2018-09-01 | 2019-06-30 | The Office of School Improvement will ensure the continued implementation of the Karen Mapp Model of Family and Community Engagement across the 16 building-level teams. Each team will enlist a host of strategies to improve parent engagement and thereby increase student achievement. | As you develop the implementation plan, consider how the activities of the Karen Mapp Model of Family and Community Engagement across the 16 building-level teams will advance the goal.

## AllocationPlan-Improvement
Financial Allocation Plan - Improvement
Improvement Set-Aside Budget Summary
District | Accountability Status | Amount of Funds Allocated for District-Level Improvement
Focus District
Name of Priority/Focus School | Accountability Status | Amount of Funds Allocated for School-Level Improvement
DISTRICT / BUILDING TOTALS |  | 0

## AllocationPlan-PE
Financial Allocation Plan - Parent Education
Parent Education Set-Aside Budget Summary
Name of Priority/Focus School | Accountability Status | Amount of Funds Allocated for Parent Education
DISTRICT / BUILDING TOTALS |  | 0

## SI Set Aside Rates (hidden)
School Improvement Set Aside Rate based on count of all schools
LEA BEDS | LEA NAME | All Schools | # of Priority & Focus Schools (minimum required) | % of identified schools | Required Set Aside % | Title III Set Aside required | Percentage of identified schools | Required Set-Aside rate
010100010000 | ALBANY CITY SD | 15 | 13 | 86.67% | 15% |  | Less than 30% | 5%
270100010000 | AMSTERDAM CITY SD | 6 | 5 | 83.33% | 15% |  | 30-34% | 6%
050100010000 | AUBURN CITY SD | 7 | 6 | 85.71% | 15% |  | 35-39% | 7%
030200010000 | BINGHAMTON CITY SD | 10 | 9 | 90% | 15% |  | 40-44% | 8%
062301040000 | BROCTON CSD | 2 | 0 | 0% | 5% |  | 45-49% | 9%
580203020000 | BROOKHAVEN-COMSEWOGUE UFSD | 6 | 0 | 0% | 5% |  | 50-54% | 10%
490202040000 | BRUNSWICK CSD (BRITTONKILL) | 2 | 1 | 50% | 10% |  | 55-59% | 11%
161601040000 | BRUSHTON-MOIRA CSD | 2 | 0 | 0% | 5% |  | 60-64% | 12%
140600010000 | BUFFALO CITY SD | 56 | 35 | 62.5% | 12% |  | 65-69% | 13%
222201060000 | CARTHAGE CSD | 5 | 1 | 20% | 5% |  | 70-74% | 14%
060401040000 | CASSADAGA VALLEY CSD | 2 | 0 | 0% | 5% |  | 75% or more | 15%
190401060000 | CATSKILL CSD | 3 | 3 | 100% | 15%
580513030000 | CENTRAL ISLIP UFSD | 8 | 4 | 50% | 10%
120401040000 | CHARLOTTE VALLEY CSD | 1 | 1 | 100% | 15%
110101040000 | CINCINNATUS CSD | 3 | 1 | 33.33% | 6%
650301040000 | CLYDE-SAVANNAH CSD | 3 | 1 | 33.33% | 6%
010500010000 | COHOES CITY SD | 5 | 0 | 0% | 5%
110200010000 | CORTLAND CITY SD | 6 | 2 | 33.33% | 6%
610301060000 | DRYDEN CSD | 5 | 2 | 40% | 8%
060800010000 | DUNKIRK CITY SD | 6 | 4 | 66.67% | 13%
500402060000 | EAST RAMAPO CSD (SPRING VALLEY) | 14 | 8 | 57.14% | 11%
180901040000 | ELBA CSD | 2 | 0 | 0% | 5%
070600010000 | ELMIRA CITY SD | 11 | 11 | 100% | 15%
590501060000 | FALLSBURG CSD | 2 | 1 | 50% | 10%
021601040000 | FRIENDSHIP CSD | 1 | 1 | 100% | 15%
460500010000 | FULTON CITY SD | 6 | 1 | 16.67% | 5%
430700010000 | GENEVA CITY SD | 4 | 3 | 75% | 15%
081401040000 | GEORGETOWN-SOUTH OTSELIC CSD | 1 | 1 | 100% | 15%
630300010000 | GLENS FALLS CITY SD | 5 | 1 | 20% | 5%
630918080000 | GLENS FALLS COMN SD | 1 | 0 | 0% | 5%
170500010000 | GLOVERSVILLE CITY SD | 6 | 4 | 66.67% | 13%
511101060000 | GOUVERNEUR CSD | 3 | 1 | 33.33% | 6%
042801060000 | GOWANDA CSD | 3 | 1 | 33.33% | 6%
010701030000 | GREEN ISLAND UFSD | 1 | 1 | 100% | 15%
610501040000 | GROTON CSD | 2 | 1 | 50% | 10%
250701040000 | HAMILTON CSD | 2 | 0 | 0% | 5%
460701040000 | HANNIBAL CSD | 3 | 3 | 100% | 15%
230301040000 | HARRISVILLE CSD | 2 | 0 | 0% | 5%
280201030000 | HEMPSTEAD UFSD | 10 | 7 | 70% | 14%
511301040000 | HERMON-DEKALB CSD | 1 | 1 | 100% | 15%
061700010000 | JAMESTOWN CITY SD | 9 | 5 | 55.56% | 11%
540901040000 | JEFFERSON CSD | 1 | 1 | 100% | 15%
031502060000 | JOHNSON CITY CSD | 4 | 2 | 50% | 10%
620600010000 | KINGSTON CITY SD | 10 | 4 | 40% | 8%
420807040000 | LAFAYETTE CSD | 3 | 0 | 0% | 5%
590901060000 | LIBERTY CSD | 2 | 2 | 100% | 15%
161501060000 | MALONE CSD | 5 | 2 | 40% | 8%
121401040000 | MARGARETVILLE CSD | 1 | 1 | 100% | 15%
541001040000 | MIDDLEBURGH CSD | 2 | 1 | 50% | 10%
051301040000 | MORAVIA CSD | 2 | 0 | 0% | 5%
240901040000 | MT MORRIS CSD | 2 | 1 | 50% | 10%
660900010000 | MT VERNON SCHOOL DISTRICT | 16 | 10 | 62.5% | 12%
650101060000 | NEWARK CSD | 5 | 2 | 40% | 8%
441600010000 | NEWBURGH CITY SD | 12 | 6 | 50% | 10%
400800010000 | NIAGARA FALLS CITY SD | 11 | 7 | 63.64% | 12%
651501060000 | NORTH ROSE-WOLCOTT CSD | 3 | 1 | 33.33% | 6%
170901040000 | NORTHVILLE CSD | 2 | 1 | 50% | 10%
411504020000 | NY MILLS UFSD | 2 | 0 | 0% | 5%
550101040000 | ODESSA-MONTOUR CSD | 3 | 0 | 0% | 5%
661500010000 | PEEKSKILL CITY SD | 6 | 3 | 50% | 10%
680601060000 | PENN YAN CSD | 3 | 1 | 33.33% | 6%
091200010000 | PLATTSBURGH CITY SD | 5 | 2 | 40% | 8%
441800050000 | PORT JERVIS CITY SD | 4 | 1 | 25% | 5%
131500010000 | POUGHKEEPSIE CITY SD | 7 | 6 | 85.71% | 15%
580602040000 | RIVERHEAD CSD | 7 | 6 | 85.71% | 15%
261600010000 | ROCHESTER CITY SD | 51 | 41 | 80.39% | 15%
043200050000 | SALAMANCA CITY SD | 3 | 2 | 66.67% | 13%
161201040000 | SALMON RIVER CSD | 4 | 1 | 25% | 5%
530600010000 | SCHENECTADY CITY SD | 17 | 14 | 82.35% | 15%
121601060000 | SIDNEY CSD | 3 | 0 | 0% | 5%
061501040000 | SILVER CREEK CSD | 3 | 0 | 0% | 5%
651201060000 | SODUS CSD | 3 | 1 | 33.33% | 6%
421800010000 | SYRACUSE CITY SD | 33 | 24 | 72.73% | 14%
491700010000 | TROY CITY SD | 7 | 2 | 28.57% | 5%
412300010000 | UTICA CITY SD | 13 | 7 | 53.85% | 10%
121901040000 | WALTON CSD | 3 | 2 | 66.67% | 13%
600101060000 | WAVERLY CSD | 5 | 1 | 20% | 5%
280401030000 | WESTBURY UFSD | 6 | 1 | 16.67% | 5%
262001040000 | WHEATLAND-CHILI CSD | 2 | 0 | 0% | 5%
170301020000 | WHEELERVILLE UFSD | 1 | 1 | 100% | 15%
472506040000 | WORCESTER CSD | 1 | 1 | 100% | 15%
580109020000 | WYANDANCH UFSD | 4 | 4 | 100% | 15%
662300010000 | YONKERS CITY SD | 39 | 10 | 25.64% | 5%
|  | 558 | 311